## App_All_Defects
Defect_Id | Type Of Issue | Priority | Issue Description | Pre Requisties | Steps To Recreate | Actual Result | Expected Result | Screenshot Reference | Tested On | Affected On | Dev Comments | Retesting as on 18-1-2018 | Dev Comments | Retestng as on 22-1-2018 | Dev Comments | Retestng as on 25-1-2018 | Dev Comments | Retestng as on 31-1-2018 | Dev Comment | Retesting as on 2-2-2018 | Retesting as on 5-2-2018 | iOS Developer's comment | Retesting as on 13-2-2018 | Dev Comment |  | Retesting as on 16-feb
1 | Functional | Medium | Incorrect validation message appears on entering number less than 10 digits, under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | Open Apni Kheti app. | 1. Enter Number less than 10 digits 2. Click on 'Submit' button 3. Observe | Please check the number' validation message appears on entering number less than 10 digits, under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | Mobile number should be of 10 digits' validation message should appear on entering number less than 10 digits, under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | http://prntscr.com/i11ts8 | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
2 | Functional | Low | User is allow to enter more than 10 digits under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | Open Apni Kheti app. | 1. Enter Number more than 10 digits 2. Observe1. Enter Number more than 10 digits 2. Observe | User is allow to enter more than 10 digits under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | User should not allow to enter more than 10 digits under 'Enter Your Mobile Number' text field, of 'Apni Kheti' login page. | http://prntscr.com/i11tha | Iphone 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
3 | Functional | Medium | Unwanted Hindi and Punjabi keypad appears for mobile number field, under 'Apni Kheti' login page. | Open Apni Kheti app. | 1. Tap on 'Enter Your Mobile Number' text field 2. Change language 3. Observe | Unwanted Hindi and Punjabi keypad appears for mobile number field, under 'Apni Kheti' login page. | Unwanted Hindi and Punjabi keypad should not appear for mobile number field, under 'Apni Kheti' login page. | http://prntscr.com/i11te3 | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
4 | UI | Low | Inconsistent validation message appears for IOS and Android, on clicking 'Submit' button after leaving 'Terms and conditions' checkbox uncheck, under 'Apni Kheti' login page. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Enter Mobile number and Leave 'Terms and Conditions' checkbox uncheck 3. Click on 'Submit' button 4. Observe 5. Now, open Apni Kheti app in IOS 6. Enter Mobile number and Leave 'Terms and Conditions' checkbox uncheck 7. Click on 'Submit' button 8. Observe | Inconsitent validation message appears as : 1. 'Please select the Term and Condition' validation message appears for 'IOS' 2. Whereas 'Please accept Terms and Condition in order to continue' validation message appears for 'Android'. | Please accept Terms and Condition in order to continue' validation message should appear. | http://prntscr.com/i11t8b | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) | Done | Still Occurring on IOS as on 18-1-2018 | Done | Verified as on 22-1-2018
5 | UI | Medium | Inconsistent validation message appears for IOS and Android, on clicking 'Submit' button after leaving 'Enter Your Mobile Number' text field blank, under 'Apni Kheti' login page. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Leave Enter Your Mobile number field blank 3. Click on 'Submit' button 4. Observe 5. Now, open Apni Kheti app in IOS 6. Leave Enter Your Mobile number field blank 7. Click on 'Submit' button 8. Observe | Inconsitent validation message appears as : 1. 'Enter your number first' validation message appears for 'IOS' 2. Whereas 'Please add mobile number first' validation message appears for 'Android'.Inconsitent validation message appears as : 1. 'Enter your number first' validation message appears for 'IOS' 2. Whereas 'Please add mobile number first' validation message appears for 'Android'. | Please add mobile number first' validation message should appear. | http://prntscr.com/i11w12 | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) |  | Still Occurring on IOS as on 18-1-2018 | Done | Verified as on 22-1-2018
6 | UI | Medium | UI issue appears under OTP page. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Enter number and Tap on Submit' button 3. Observe the OTP page 4. Repeat above steps on IOS and Observe the OTP page | 1. Inconsistent place holder text appears in IOS and Android respectively 2. OTP appears in small case under 'Didn't receive the Otp?' text under IOS. 3. Label of Submit button appears in small case in IOS whereas it appears in upper case in Android. 4. Image on the top of the page has different sizes in IOS and Android. | 1. 'Enter OTP' place holder text should appear in IOS 2. OTP should appears in upper case under 'Didn't receive the Otp?' text under IOS. 3. Label of Submit button should appear in upper case. 4. Image on the top of the page should be of same size as in android. | http://prntscr.com/i12mzw | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) |  | Still Occurring on IOS as on 18-1-2018 | Done | Still Occurring as 'Image on the top of the page should be of same size as in android.' | I have check in android image size is same it depend upon screen size also please check it on same screen size and tell us if you still found the issue | Still Occurring 1. Content under OTP page appear small as compare to image, on IOS that is looking quite different. So, decrease the size of the image 2. Content under OTP page should be centrally aligned in IOS and Android. | Done | Still Occurring as Content under OTP page should be centrally aligned in Android. |  |  | Still Occurring on Android |  |  | Done |  | Still Occurring as content under OTP page on IOS and Android is not consistent.
7 | Functional | Medium | No confirmation message appears after clicking on 'Resend Code' link, under 'OTP' page. | Open Apni Kheti app. | 1. Open Apni Kheti app 2. Enter number and Tap on Submit' button 3. Tap on 'Resend Code' link on OTP page 4. Observe | No confirmation message appears after clicking on 'Resend Code' link, under 'OTP' page. | Confirmation message should appear after clicking on 'Resend Code' link, under 'OTP' page. | http://prntscr.com/i13fhh | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11), Android 7 | Done | Verified on IOS but Still Occurring on Android | Done | Verified as on 22-1-2018
8 | UI | Low | UI issue appear in the email of reffered friend, only on IOS | User has logged in into his account. | 1. Click on Refer Now button 2. Select 'Mail' option 3. Enter email address of the friend 4. Click on 'Send' button 5. Open email id of the referred friend 6. observe the message | UI issue appear in the email of reffered friend. | UI issue should get resolved. | http://prntscr.com/i13hfw | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11), Android 7 | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
9 | Functional | Medium | Nothing happens on clicking 'Submit' button after entering number less than 10 digits and entering invalid email, after selecting any other country, under 'Apni Kheti Login' page. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Select any other country 3. Enter number less than 10 digits 4. Enter invalid email 5. Click on Submit' button 6. Observe | Nothing happens. | 1. 'Mobile number should be of 10 digits' validation message should appear for mobile number field 2. 'Enter Correct Email' validation message should appear for Email field after entering invalid email | http://prntscr.com/i11z20 | Iphone 6, 6s(IOS 11), Android 7 | Android 7 | Done | Still Occurring on Android. | Done | Verified as on 22-1-2018
10 | Functional | Medium | Inconsistent validation message appears on entering invalid OTP under OTP page, on 'Android' and 'IOS'. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Enter number and Tap on Submit' button 3. Enter incorrect OTP 4. Tap on Submit button 5. Observe the validation message 6. Repeat above steps on IOS and Observe the validation | Inconsistent validation message appears on entering invalid OTP under OTP page, on 'Android' and 'IOS'. | Please check the OTP' validation message should appear on entering invalid OTP under OTP page, on 'Android' | http://prntscr.com/i1259t | Iphone 6, 6s(IOS 11), Android 7 | Android 7 | Done | Still Occurring on Android. | Done | Verified as on 22-1-2018
17-1-2018
11 | Functional | High | Site crashes on tapping under 'Select Village' drop down when no village list appears, under 'My Profile' page. | 1. User has logged in into his account. 1. User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Select State>>Himachal Pradesh, District>>Bilaspur, Tehsil>>Bilaspur 3. Tap on 'Select Village' drop down 4. Observe | Site crashes on tapping under 'Select Village' drop down when no village list appears, under 'My Profile' page. | Site should not crash on tapping under 'Select Village' drop down when no village list appears, under 'My Profile' page. | http://prntscr.com/i1m2y6 | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11) | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
12 | Functional | Medium | No validation message appears on clicking 'Submit' button after entering invalid email under 'My Profile' page. | 1. User has logged in into his account. 1. User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Fill data in all mandatory fields and enter invalid email address 3. Tap on 'Submit' button and Observe | No validation message appears on clicking 'Submit' button after entering invalid email under 'My Profile' page. | Proper validation message should appear on clicking 'Submit' button after entering invalid email under 'My Profile' page. | http://prntscr.com/i1m23o | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11),Android 7 | Done | Verified on IOS but Still Occurring on Android | Done | Verified as on 22-1-2018
13 | UI | Low | Chandigarh option appears twice under 'Select Tehsil' drop down of 'My Profile' page. | 1. User has logged in into his account. 1. User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Fill data in all mandatory fields 3. Select State and District >> Chandigarh 4. Observe the Tehsil Drop down | Chandigarh option appears twice under 'Select Tehsil' drop down of 'My Profile' page. | Chandigarh option should not appear twice under 'Select Tehsil' drop down of 'My Profile' page. | http://prntscr.com/i1m1ua | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11),Android 7 | Done | Verified as on 18-1-2018 |  | Still Occurring on Android. | As I told you in this field we got chandigarh twice form api respponse . |  |  |  | Please Ask this To Backend person | Closed
14 | Functional | Low | Selected Tehsil get disappear after submitting My Profile information. | 1. User has logged in into his account. 1. User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Fill data in all mandatory fields 3. Select State, District and Tehsil 4. Submit the information 5. Now, again tap on 'My Profile' icon 6. Observe | Selected Tehsil get disappear after submitting My Profile information. | Selected Tehsil should not get disappear after submitting My Profile information. | http://prntscr.com/i1m1i7 | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11) | Done | Verified as on 18-1-2018 |  | Verified as on 22-1-2018
15 | Functional | Low | Image disappears on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | 1. User has logged in into his account. | 1. Tap on 'Live Stock' icon 2. Select 'HF(HOLSTEIN FRESIAN) cow 3. Tap on 'Diseases and Treatment' tab 4. Scroll down the section 5. Scroll up the section and Observe the image | Image disappears on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | Image should not get disappear on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | http://prntscr.com/i1m10d | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11) | I am not doing anything is this i just show the link in webview it is not from my side | We have checked the web view link in Safari browser and it is working fine. It is also working fine in Android browser and Android App. |  | Mohit Kindly Comment. |  | Still Occurring as on 25-1-2018 | it Is coming in ios version 11 not in lower version we found some olution because it is unexpected issue | Still Occurring. This issue should get resolve for latest versions ASAP. | Still working on this did'nt find the solution will update you asap | Still Occurring as on 2-2-2018 | Verified as on 5-2-2018
16 | Functional | Medium | No validation message appears on clicking 'Submit' button after entering invalid reference code under 'Reference Code' pop up. | New user has logged in into his account. | 1. Enter incorrect Reference code' 2. Click on 'Submit' button 3. Observe | No validation message appears on clicking 'Submit' button after entering invalid reference code under 'Reference Code' pop up. | Proper validation message should appear on clicking 'Submit' button after entering invalid reference code under 'Reference Code' pop up. | http://prntscr.com/i1m3ex | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11),Android 7 | Done | Verified on IOS but Still Occurring on Android | Done | Verified as on 22-1-2018 |  | Verified as on 25-1-2018
18-1-2017
17 | Functional | Medium | Functional issues appear under 'Video' section of 'Preview Files' page, under 'Q&A' tab. | Expert has logged in into his account. | 1. Tap on Q&A section 2. Tap on Question 3. Write an answer 4. Attach a video 5. Now tap on 'Preview Files' link 6. Play a video 7. Observe | 1. User is not able to stop the video 2. Progress bar is not working 3. Time section does not appear 4. Zoom Video icon is not functional 5. Sound Icon is not functional. | 1. User should be able to stop the video 2. Progress bar should be working 3. Time section should appear 4. Zoom Video icon should be functional 5. Sound Icon should be functional. | http://prntscr.com/i20uvi | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done |  |  | Verified as on 22-1-2018
18 | Functional | Medium | Preview Files' option is missing under 'Attach' pop up of 'Q&A' section page, only on Android | Expert has logged in into his account. | 1. Tap on Q&A section 2. Tap on Question 3. Write an answer 4. Tap on Attach file icon 5. Observe | Preview Files' option is missing under 'Attach' pop up of 'Q&A' section page, only on Android | Preview Files' option should appear under 'Attach' pop up of 'Q&A' section page, only on Android | http://prntscr.com/i20ru6 | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Android 7 | Done |  |  | Still Occurring on Android only on 22-10-2018 | Done | Verified as on 25-1-2018
19 | Functional | Medium | Null value appears instead of name of the user who has posted the question, under 'Q&A' page. | Expert has logged in into his account. | 1. Tap on Q&A section 2. Scroll down the page and Observe | Null value appears instead of name of the user who has posted the question, under 'Q&A' page. | User name should appear instead of Null value, under 'Q&A' page. | http://prntscr.com/i212q9 | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Server End |  |  | Still occurring.This is not from server end. Please resolve it ASAP. | As discussed in group it is not from our side |  |  |  | Please ask this to backend persion it is not from my end and please close this if backend person fix this issue | Closed
20 | UI | Medium | Inappropriate validation message appears on trying to select more than 4 photos under 'Ask Question' section of 'Q&A' page, only on Android | Expert has logged in into his account. | 1. Tap on Q&A section 2. Tap on Ask Question button 3. Tap on 'Upload a Image' icon 4. Select 'Choose From Gallery' link 5. Try to select more than 4 photos 6. Observe the validation message. | Validation message appears as 'Select Images amount is limit' on trying to select more than 4 photos under 'Ask Question' section of 'Q&A' page,only on android | Validation message should appear as 'Only 4 photos please! You can only send 4 photos at a time' | http://prntscr.com/i21hye | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Android 7 | Done |  |  | Verified as on 22-1-2018
21 | UI | Medium | Confirmation message appears in english on clicking 'Resend Code' link, even after selecting Hindi/ Punjabi language under 'OTP' page. | Open Apni Kheti app. | 1. Select Hindi language 2. Enter mobile number 3. Tap on 'Submit' button 4. Tap on Resend OTP link 5. Observe | Confirmation message appears in english on clicking 'Resend Code' link, even after selecting Hindi/ Punjabi language under 'OTP' page. | Confirmation message should appear in Hindi or Punjabi on clicking Resend OTP link, after selecting Hindi/ Punjabi language under 'OTP' page. | http://prntscr.com/i21zq0 | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done |  |  | Verified as on 22-1-2018
22 | UI | Medium | Confirmation message appears in english even after selecting 'Punjabi' language, which appears on clicking 'Submit' button after entering incorrect email , under Apni Kheti Login page. | 1. Open Apni Kheti app. 2. User has selected Punjabi language 3. User has selected any other country | 1. Select any other country 2. Enter email in invalid format 3. Tap on 'Submit' button 4. Observe the confirmation message. | Confirmation message appears in english even after selecting 'Punjabi' language, which appears on clicking 'Submit' button after entering incorrect email , under Apni Kheti Login page. | Confirmation message appears in punjabi after selecting 'Punjabi' language, which appears on clicking 'Submit' button after entering incorrect email , under Apni Kheti Login page. | http://prntscr.com/i224ui | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done |  |  | Verified as on 22-1-2018
23 | UI | Medium | Validation message appears in english even after selecting Punjabi language, which appears on clicking 'Submit' button after entering invalid email under 'My Profile' page | 1.User has logged in into his account. 2. User has selected Punjabi language | 1. Tap on 'My Profile' icon 2. Enter invalid email and tap on 'Submit'button 3. Observe validation message | Validation message appears in english even after selecting Punjabi language, which appears on clicking 'Submit' button after entering invalid email under 'My Profile' page | Validation message should appear in punjabi on selecting Punjabi language, which appears on clicking 'Submit' button after entering invalid email under 'My Profile' page | http://prntscr.com/i229ev | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done |  |  | Verified as on 22-1-2018
22-1-2018
24 | Functional | High | Select Language' pop up does not appear on opening Apni Kheti app, only on Android | Open Apni Kheti app on Android. | 1. Observe | Select Language' pop up does not appear on opening Apni Kheti app, only on Android | Select Language' pop up should appear on opening Apni Kheti app, only on Android | http://prntscr.com/i3uknq | Iphone 6(IOS 11.2), 6s(IOS 11.1), Android 7 | Andorid 7 |  |  |  |  | Done | Verified as on 25-1-2018
25 | Functional | Medium | Image disappears on opening update, under 'Updates' section. | User has logged in into his account. | 1. Tap on 'Updates' icon 2. Tap on update specified in the screenshot 3. Observe | Image disappears on opening update, under 'Updates' section. | Image should not disappear on opening update, under 'Updates' section. | http://prntscr.com/i242fd | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) |  |  |  |  | Done | Verified as on 25-1-2018
26 | UI | Medium | UI issue appears under Post Advisory page. | 1. Expert has logged in into his account. 2. Expert has selected Hindi Language | 1. Tap on 'Post Advisory' tab under left side panel 2. Observe Placeholder text for text field 3. Now, fill all mandatory fields and leave Text mandatory field blank 4. Tap on 'Submit' button 5. Observe 6. Now select language 'Punjabi' 7. Tap on 'Post Advisory' tab 8. Observe the Placeholder text for State field and 'Text' field. 9. Leave State field blank 10. Tap on Submit button and Observe Validation message. | UI issue appears under Post Advisory page. | UI issue should get resolved as shown in attached screenshot. | http://prntscr.com/i3rp1n | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). |  |  |  |  | Done | Still Occurring. Screenshot Reference: http://prntscr.com/i59p7e | Done | Verified as on IOS on 31-1-2018 Still Occurring on Android. |  |  | Verified as on 5-2-2018
27 | Functional | High | Site crashes after loggin into the account. | User has entered Otp and Tapping on Submit button | 1. Observe | Site crashes after loggin into the account. | Site should not crash after loggin into the account. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) |  |  |  | Verified as on 22-1-2018 | Done |  |  | Verified as on 31-1-2018
28 | Functional | Medium | Notification' count beyond 99 is not increasing , under Notification bell icon. | Expert has logged in into his account. | 1. Observe 'Notification' count after 99 count. | Notification' count beyond 99 is not increasing , under Notification bell icon. | Notification' count beyond 99 should increase , under Notification bell icon. | http://prntscr.com/i3ue60 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) |  |  |  |  | in this we have show + sign when notification ocunter greater than 99 as disscussed with hunar sir | Still Occurring as on 25-1-2018 | Done |  | Please check this I have done this issue . | Verified.
29 | Functional | High | Posted advisory by expert does not appear under 'Advisory' subtab of 'Updates'tab. | Expert has logged in into his account. | 1. Tap on 'Post Advisory' tab under left side panel 2. Post a advisory 3. Observe the posted advisory under 'Advisory' section of Apni Kheti' app. | Submitted Succesfully' Cofirmation message appears but posted advisory does not appear under 'Advisory' subtab. | Posted advisory by expert should appear under 'Advisory' subtab of 'Updates'tab. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). |  |  |  |  | Done | Still Occurring as on 25-1-2018 | as discussed on phone . It is shown on advisory section | Verified on IOS but Still Occurring on Android. |  |  | Verified as on 5-2-2018
30 | Functional | Medium | No data to display' message appears and Posted advisory through admin does not appear under 'Advisory' section, only on IOS. | Expert has logged in into his account. | 1. Tap on 'Advisory' subtab of 'Updates' tab. 2. Observe | No data to display' message appears and Posted advisory through admin does not appear under 'Advisory' section, only on IOS. | Posted advisory through admin should appear under 'Advisory' section, only on IOS. | http://prntscr.com/i3uy8m | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) |  |  |  |  | Done | Still Occurring as on 25-1-2018 | as discussed on phone . It is shown on advisory section\ | Verified as on 31-1-2018
31 | Functional | Medium | Inconsistent 'Unfortunately, Apni Kheti has stopped' validation pop up opens up on leaving phone in Ideal State, only on Android. | Expert has logged in into his account. | 1.Leave phone in Ideal state 2. Observe | Inconsistent 'Unfortunately, Apni Kheti has stopped' validation pop up opens up on leaving phone in Ideal State, only on Android. | Unfortunately, Apni Kheti has stopped' validation pop up should not appear on leaving phone in Ideal State, only on Android. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). |  |  |  |  | Unable to create this issue |  |  |  | Still Occurring as on 1-2-2018
25-1-2018
32 | Ui | Medium | Incorrect validation message appears on clicking 'Submit' button after leaving Reply field blank, under 'Q&A' page. | User has posted a question. | 1. Expert has answered the question. 2. User has commented on it 3. Now, tap on 'Reply' icon 4. Tap on 'Submit' button after leaving Reply field blank 5. Observe the validation message. | Please write your comment' validation message appears on clicking 'Submit' button after leaving Reply field blank, under 'Q&A' page. | Appropriate validation message should appear on clicking 'Submit' button after leaving Reply field blank, under 'Q&A' page. | http://prntscr.com/i4bbta | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Verified as on 31-1-2018
33 | Functional | Medium | Page scrolls down automatically after clicking on 'My Profile' tab, only on Android. | User has logged in into his account. | 1. Tap on 'My Profile' tab. 2. Observe | Page scrolls down automatically after clicking on 'My Profile' tab, only on Android. | Page should not get scrolled down after clicking on 'My Profile' tab, only on Android. | http://prntscr.com/i4b6rf | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
34 | UI | Medium | Constrain' option does not appear after uploading profile image under 'My Profile' page, only on Android. | User has logged in into his account. | 1. Tap on 'My Profile' tab. 2. Upload an image from gallery 3. Observe | Constrain' option does not appear after uploading profile image under 'My Profile' page, only on Android. | Constrain' option should appear after uploading profile image under 'My Profile' page, only on Android. | http://prntscr.com/i4cf0l | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
35 | Functional | High | Updated profile image does not appear on another phone for the same user, under 'My Profile' page. | Same user has logged in in two devices. | 1.Tap on 'My Profile' tab. 2. Upload an image from gallery 3. Tap on 'Submit' button 4. Now observe the profile image on another phone. | Updated profile image does not appear on another phone for the same user, under 'My Profile' page. | Updated profile image should appear on another phone for the same user, under 'My Profile' page. | http://prntscr.com/i4exij | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
36 | UI | Low | Tabs on left side panel are placed in different sequence on IOS and Android. | User has logged in into his account. | 1. Tap on Hamburger icon 2. Observe the tabs sequence in IOS and Android. | Tabs on left side panel are placed in different sequence on IOS and Android. | Tabs on left side panel should placed in same sequence on IOS and Android. | http://prntscr.com/i4datp | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Done | [14 empty] | Verified
37 | Functional | Medium | Validation message appears on leaving non mandatory 'District' field blank , under 'Post Advisory' page, only on IOS | Expert has logged in into his account. | 1. Tap on 'Post Advisory' tab on left side panel 2. Leave district field blank and fill all other mandatory fields 3. Tap on 'Submit' button 4. Observe | Please select state and district.' validation message appears on leaving non mandatory 'District' field blank, under 'Post Advisory' page. | No such validation message should appear on leaving 'District' field blank as it is not a mandatory field, under 'Post Advisory' page. | http://prntscr.com/i59f5d | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | it is mandetory that’s why I show the validation message | [6 empty] | Still Occurring as District field is not mandatory please resolve this issue. | Done | Verified as on 2-2-18 | Still Occurring on IOS as on 5-2-2018 | DONE | Verified as on IOS
29-1-2018
38 | UI | Medium | Unwanted text appears in notification received about advisory, only on Android | 1. User has posted a question 2. Expert has answered a question | 1.User received a notification 2. Observe | Unwanted text appears in notification received about advisory, only on Android | No such unwanted text should appear in notification received about advisory, only on Android | http://prntscr.com/i5adwk | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [7 empty] | Still Occurring on Android.
39 | Functional | High | Null Values appear after tapping on 'Weather' icon. | New user has logged in into his account. | 1. Enter all profile information 2. Tap on 'Weather' icon 3. Observe | Null Values appear after tapping on 'Weather' icon. | Null Values should not appear after tapping on 'Weather' icon. | http://prntscr.com/i701ak | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Resolve all the UI issues regarding this page 1. Place degree icon with 27 2. Screenshot Reference: http://prntscr.com/i7zucx | Right now we just show the dummy data and in next screen Shot to change the dummy data in all translation. | Not getting your point. | Verified as on 5-2-2018
40 | UI | Low | Heading appears in English even after selecting hindi or punjabi language, under Reference Code pop up. | 1. User has selected Hindi language and New user has logged in into his account. | 1. Observe the reference code heading. | Heading appears in English even after selecting hindi or punjabi language, under Reference Code pop up. | Heading should appears in hindi or punjabi on selecting hindi or punjabi language, under Reference Code pop up. | http://prntscr.com/i701w9 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Refer kiya code' header text appears instead of Reference code in Hindi. | Please Provide the translation because I got this hindi translation from your team. | Still occurring Text: रेफरन्स कोड | Verified as on 5-2-2018
41 | Functional | Medium | User is able to 'Skip'after tapping continuously on 'Skip' link, under 'My Profile' page. | User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Observe | User is able to 'Skip'after tapping continuously on 'Skip' link, under 'My Profile' page. | User should be able to 'Skip'after tapping once on 'Skip' link, under 'My Profile' page. | http://prntscr.com/i701zr | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Verified as on 31-2-2018
42 | UI | Low | Skip' appears in english even after selecting 'Hindi' language, under 'My Profile' page. | User has selected Hindi language | 1. User has logged in into his account. 2. Tap on 'My Profile' icon 3. Observe | Skip' appears in english even after selecting 'Hindi' language, under 'My Profile' page. | Skip' should appear in hindi after selecting 'Hindi' language, under 'My Profile' page. | http://prntscr.com/i702yn | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Verified as on 31-2-2018
43 | Functional | Medium | States list for new user appears in english even after selecting Punjabi language under 'My Profile' page. | User has selected punjabi language | 1. User has logged in into his account. 2. Tap on 'My Profile' icon 3. Tap on 'State' drop down and Observe | States list for new user appears in english even after selecting Punjabi language under 'My Profile' page. | States list for new user should appear in punjabi after selecting Punjabi language under 'My Profile' page. | http://prntscr.com/i707we | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | Not fom our side serve side | [7 empty] | This is not form our end please ask backend person for this . | Verified as on 2-2-18
30-1-2018
44 | Functional | High | Attached document does not appear along with answer after answering a question. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Observe the answer sent by expert. | Attached document does not appear along with answer after answering a question. | Attached answer document should appear after answering a question. | http://prntscr.com/i7hoh8 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | New |  | Still Occuring on Both as on 5-2-2018 | Already Done at my end, backend need to update the code | Still Occurring on Both | Already Done on Both |  | Still Occurring http://prntscr.com/iffs8c
45 | Functional | Medium | Default video and audio appears under 'Preview Files' page after attaching document, under 'Q&A' section. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Tap on 'Preview files' tab 2. Observe | Default video and audio appears under 'Preview Files' page after attaching only document, under 'Q&A' section. | Preview Files' option should disappear after attaching only document, under 'Q&A' section. | http://prntscr.com/i7hws5 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Working on it |  | NOTE: 'Preview Files' option should disappear after attaching only document, under 'Q&A' section. | Done | Verified as on IOS
46 | Functional | Medium | Close' icon still appears after removing the attached document, under 'Attach' pop up of 'Q&A' section. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Tap on 'Close' icon of attached document 2. Remove the document and Observe | Close' icon still appears after removing the attached document, under 'Attach' pop up of 'Q&A' section. | Close' icon should not appear after removing the attached document, under 'Attach' pop up of 'Q&A' section. | http://prntscr.com/i7i0eu | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Woking on it |  | Verified as on 5-2-2018
47 | UI | Medium | Sun appears even after weather is cloudy or rainy, under 'Forecast Weather' page. | User has logged in into his account. | 1. Tap on 'Weather' icon 2. Select Location and Observe | Sun appears even after weather is cloudy or rainy, under 'Forecast Weather' page. | Sun should not appear when weather is cloudy or rainy, under 'Forecast Weather' page. | http://prntscr.com/i7l5oy | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | New work |  | Verified as on 5-2-2018
31-1-2018
48 | Functional | High | Posted advisory by expert appears many time, under Advisory page. | Expert has logged in into his account. | 1. Expert has posted a advisory 2. Now, Go to Updates 3. Tap on 'Advisory' tab 4. Observe | Posted advisory by expert appears many time, under Advisory page. | Posted advisory by expert should not appear many time, under Advisory page. | http://prntscr.com/i7zo4l | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Not From our end Plerase Ask Backend person | Verified as on 2-2-2018
49 | UI | Low | Full stop appears in the end of validation message, under Post Advisory page. | Expert has logged in into his account and has selected hindi language. | 1. Expert is on Post Advisory page 2. Leave Advisory field blank and fill all other mandatory fields 3. Tap on submit button and Observe | Full stop appears in the end of validation message, under Post Advisory page. | Full stop should not appear in the end of validation message, under Post Advisory page. | http://prntscr.com/i7zo9k | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Verified as on 2-2-2018
50 | Functional | High | On selecting single district some other districts get selected automatically, under 'Post Advisory' page only on IOS. | Expert has logged in into his account. | 1. Expert is on Post Advisory page 2. fill all mandatory fields and select State>>Punjab, District>> Amritsar 3. observe Ferozpur , Mansa and Sangrur districts | On selecting single district some other districts get selected automatically, under 'Post Advisory' page only on IOS. | Only selected district should get checked, under 'Post Advisory' page only on IOS. | http://prntscr.com/i80dl6 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), | [8 empty] | Done | Verified as on 2-2-2018
51 | UI | Medium | Irrelevant validation message appears on leaving Region field blank, under 'Share Your Story With Us' page. | Expert has logged in into his account and selected Hindi/Punjabi lanugage | 1. Expert is on 'Share Your Story With Us' page. 2. fill all mandatory fields and Leave Region field blank 3. Tap on 'Submit' button and Observe | Irrelevant validation message appears on leaving Region field blank, under 'Share Your Story With Us' page. | Appropriate validation message should appear on leaving Region field blank, under 'Share Your Story With Us' page. | http://prntscr.com/i83n10 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Done | Still Occurring as on 2-2-2018 | Still Occurring for punjabi language on IOS and Android. | DONE | Verified on IOS | Done on android |  | Verified.
52 | Functional | Medium | No validation message appears on entering invalid mobile number, under 'Share Your Story With Us' page. | Expert has logged in into his account | 1. Expert is on 'Share Your Story With Us' page. 2. fill all mandatory fields and enter invalid number 3. Tap on 'Submit' button and Observe | No validation message appears on entering invalid mobile number, under 'Share Your Story With Us' page. | Proper validation message should appear on entering invalid mobile number, under 'Share Your Story With Us' page. | http://prntscr.com/i83jbb | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [8 empty] | Done | Verified as on 2-2-2018 | [5 empty] | Verified.
53 | UI | Medium | Unwanted tags appear in notification received under 'Notification' page of user only on Android. | Expert has logged in into his account | 1. Another expert has posted a advisory 2. Tap on Notification and Observe | Unwanted tags appear in notification received under 'Notification' page of user only on Android. | Unwanted tags should not appear in notification received under 'Notification' page of user only on Android. | http://prntscr.com/i83kao | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [10 empty] | Verified as on 5-2-2018
54 | UI | Medium | Inconsistent button appears on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | Expert has logged in into his account | 1. Tap on Hamburger icon on Android 2. Tap on Settings tab 3. Tap on Logout button and Observe 4. Repeat above steps on IOS. | Inconsistent button appears on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | Consistent button should appear on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | http://prntscr.com/i83rvr | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Done | Verified as on 2-2-2018
55 | UI | Medium | Spelling mistake appears in validations, under 'Share Your Story With Us' page. | Expert has logged in into his account | 1. Expert is on 'Share Your Story With Us' page. 2. fill all fields and leave mobile number and donot upload image 3. Tap on Submit button and Observe | Spelling mistake appears in validations, under 'Share Your Story With Us' page. | Spelling mistake should not appear in validations, under 'Share Your Story With Us' page. | http://prntscr.com/i83wzh | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Done Eralier text is provide by your team | Still occurring for name field. | Verified as on 5-2-2018
56 | UI | Medium | UAR' appears in english even after selecting Hindi/Punjabi, under Header of the page. | Expert has logged in into his account | 1. Select Hindi /Punajbi Language 2. Observe the UAR section. | UAR' appears in english even after selecting Hindi/Punjabi, under Header of the page. | UAR' should not appear in english after selecting Hindi/Punjabi, under Header of the page. | http://prntscr.com/i840hz | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Right now using the image for uar please provide us the image in all threen language. | Closed
43102
57 | UI | Medium | Page header appears in english even after selecting Hindi/Punjabi language, under 'Share Your Story With Us' page. | Expert has logged in into his account and has selected hindi language. | 1. Expert is on 'Share Your Story With Us' page. 2. Observe | Page header appears in english even after selecting Hindi/Punjabi language, under 'Share Your Story With Us' page. | Page header should appear in Hindi/Punjabi after selecting Hindi/Punjabi language, under 'Share Your Story With Us' page. | http://prntscr.com/i84h5y | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Right now using the image for uar please provide us the image in all threen language. | Still Occurring as on 2-2-2018 | Verified as on 5-2-2018
58 | Functional | Medium | Attached document does not appear under Preview Files of Post Advisory page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields and attach a document 3. Tap on 'Preview Files' button and Observe | Attached document does not appear under Preview Files of Post Advisory page. | Attached document should appear under Preview Files of Post Advisory page. | http://prntscr.com/i8hvsl | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [8 empty] | Done | Still Occurring as on 2-2-2018 | Closed
59 | UI | Low | Close icon does not appear under 'Upload a Document' section after attaching any document, under 'Post Advisory' page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields and attach a document 3. Try to delete the attached document and Observe | Close icon does not appear under 'Upload a Document' section after attaching any document, under 'Post Advisory' page. | Close icon should appear under 'Upload a Document' section after attaching any document, under 'Post Advisory' page. | http://prntscr.com/i8huq7 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Verified as on 2-2-18 | Verified as on 5-2-2018
60 | UI | Medium | Selected state does not appear selected under 'State' drop down field of Post Advisory page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields and select a state 3.Observe | Selected state does not appear selected under 'State' drop down field of Post Advisory page. | Selected state should appear selected under 'State' drop down field of Post Advisory page. | http://prntscr.com/i8huh9 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Verified as on 2-2-18
61 | Functional | Medium | New counter starts from previous ended recorded counter on uploading a new audio, under 'Upload a audio' section of 'Post Adviosyr' page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields and Upload a audio 3.Now, again tap on Upload a audio icon 4. Tap on Record Audion link 5. Observe the count. | New counter starts from previous ended recorded counter on uploading a new audio, under 'Upload a audio' section of 'Post Adviosyr' page. | New counter should start from zero again on uploading a new audio, under 'Upload a audio' section of 'Post Adviosyr' page. | http://prntscr.com/i8hv3u | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Still Occurring as on 2-2-2018 | Verified as on 5-2-2018
62 | Functional | High | States and district appears many time after changing a state or district, under 'Post Advisory' page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields 3. Select State and District 4. Tap on Submit button 5. Again select another State and Distict 6. Tap on Submit button and Observe the State drop down. | States and district appears many time after changing a state or district, under 'Post Advisory' page. | States and district should not appear many time after changing a state or district, under 'Post Advisory' page. | http://prntscr.com/i8hvza | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Still Occurring Screenshot Reference: http://prntscr.com/i919ew | Verified as on 5-2-2018
63 | Functional | High | Can't play this video' validation message appears on playing a advisory video, only on android. | Expert has added a advisory | 1. Open a advisory and try to play added advisory video. | Can't play this video' validation message appears on playing a advisory video. | No such validation message should appear on playing a advisory video. | http://prntscr.com/i8hzj8 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [8 empty] | Link Which is coming from server is not working please check this : http://www.apnikheti.com/upload/advisosryVideo/idea9920180201181420.mp4 | Still Occurringon Android. | Verified as on 5-2-2018
64 | Functional | High | Loading icon continuoulsy appears on playing advisory video only on IOS. | Expert has added a advisory | 1. Open a advisory and try to play added advisory video. | Loading icon continuoulsy appears on playing advisory video only on IOS. | Loading icon should not appear on playing advisory video only on IOS. | http://prntscr.com/i8i0lq | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Link Which is coming from server is not working please check this : http://www.apnikheti.com/upload/advisosryVideo/idea9920180201181420.mp4 | It is working fine on IOS but is not working in Android. | Verified as on 5-2-2018
65 | UI | Medium | Colun and Commas are missing to separate State and Districts, under 'Post Advisory' page only on Android. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields 3. Select State and DistrictS 4. Observe the State drop down. | Colun and Commas are missing to separate State and Districts, under 'Post Advisory' page only on Android. | Colun and Commas should appear to separate State and Districts, under 'Post Advisory' page only on Android. | http://prntscr.com/i8hzmj | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [10 empty] | Verified as on 5-2-2018
66 | Functional | High | Error pop up opens up on posting a advisory after attaching images, audio and video, under 'Post Advisory' page. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields 3. Select State and DistrictS 4. Attach images, audio and videos 5. Tap on 'Submit' button and Observe | Advisory gets posted but Error pop up opens up on posting a advisory after attaching images, audio and video, under 'Post Advisory' page. | No such error pop up should open up on posting a advisory after attaching images, audio and video, under 'Post Advisory' page. | http://prntscr.com/i8i2w9 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Error I scomming from server in response some king of otice is coming please check this : ......''''''''<br /> <b>Notice</b>: Undefined variable: district_id in <b>/var/www/vhosts/apnikheti.com/httpdocs/apnikheti-version9/send_advisory.php</b> on line <b>147</b><br /> {"status":200} | Still Occurring | Verified as on 5-2-2018
67 | Functional | High | Same image appears even on selecting different images during advisory posting. | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields 3. Select State and DistrictS 4. Attach multiple images 5. Tap on 'Submit' button 6. Now, observe the images under posted advisory | Same image appears even on selecting different images during advisory posting. | Only Sent image should appear during advisory posting. | http://prntscr.com/i8i5ba | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [8 empty] | This is also from Server end but I have added Code at my end also please ask backend person also to change the code . | Verified as on 2-2-2018
68 | Functional | High | Advisory does not fit to screen when images, audio and video have been attached with it, only on IOS | Expert has logged in into his account. | 1. Expert is on 'Post Advisory' page 2. Enter data in all mandatory fields 3. Select State and DistrictS 4. Attach multiple images 5. Tap on 'Submit' button 6. Now, observe the images under posted advisory on IOS | Advisory does not fit to screen when images, audio and video have been attached with it, only on IOS | Advisory should fit to screen when images, audio and video have been attached with it, only on IOS | http://prntscr.com/i8i7f1 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [8 empty] | Done | Verified as on 2-2-2018
69 | Functional | High | Safari cannot open the page because the address is invalid' validation message appears when user opens the advisory link received through whatsapp/Email | Advisory is shared to one of a friend who has not installed Apni Kheti app. | 1. User is trying to open url and Observe the message. | Safari cannot open the page because the address is invalid' validation message appears when user opens the advisory link received through whatsapp/Email | No such validation message should appear when user opens the advisory link received through whatsapp/Email | http://prntscr.com/i8ljrs | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Same issue appears for Android as link does not open up | [7 empty] | It is in the deeplink error please provide the link which you shared so that we can check this is from my end or server end . Please Also tell us link is shared from ios to android or vice versa or ios to ios . | Link is shared from IOS to IOS and Android to Andorid and IOS to Android as well. Link Reference: http://tinyurl.com/yc9ntcu4 | Still Occurring on both as on 5-2-2018 | Already discussed with Amit | Still Occurring
2/Febb
70 | UI | Medium | Cancel button appears in english, even after selecting Hindi under LogOut confirmation pop up. | User has logged in into his account and has selected Hindi language. | 1. Tap on 'Settings' tab 2. Tap on 'Log Out' option 3. Observe | Cancel button appears in english, even after selecting Hindi under LogOut confirmation pop up. | Cancel button should appear in hindi, after selecting Hindi under LogOut confirmation pop up. | http://prntscr.com/i90bwy | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Verified as on 5-2-2018
71 | Functional | High | Selected district disappears on scrolling down the District list, under 'Post Advisory' page, only on IOS. | Expert has logged in into his account. | 1. Expert is on Post Advisory page 2. Select State 3. Select District>>Amritsar 4. Scroll down the list 5. Observe the selected district. | Selected district disappears on scrolling down the District list, under 'Post Advisory' page, only on IOS. | Selected district should not disappear on scrolling down the District list, under 'Post Advisory' page, only on IOS. | http://prntscr.com/i90b2p | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Verified as on 5-2-2018
72 | Enhancement | Medium | Replace 'Posted By:' text with ':-' text, under Latest Updates page. | Expert has logged in into his account. | 1. Expert is on Latest Updates page 2. Observe | Replace 'Posted By:' text with ':-' text, under Latest Updates page. | Replace 'Posted By:' text with ':-' text, under Latest Updates page. | http://prntscr.com/i903ig | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [10 empty] | Verified as on 5-2-2018
73 | UI | Medium | Irrelevant validation message appears on clicking Submit button without adding image, under 'Share Your Story With Us' page. | Expert has logged in into his account and selected Hindi/Punjabi lanugage | 1. Expert is on 'Share Your Story With Us' page. 2. fill all mandatory fields and Leave photo field blank 3. Observe | Irrelevant validation message appears on clicking Submit button without adding image, under 'Share Your Story With Us' page. | Appropriate validation message should appear on clicking Submit button without adding image, under 'Share Your Story With Us' page. | http://prntscr.com/i90tnv | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Still Occurring as on 5-2-2018 | Done | Verified on IOS
74 | Functional | Medium | Expert is able to open State and District drop down at same time, under Post Advisory page. | Expert has logged in into his account. | 1. Expert is on Post Advisory page 2. Select State 3. Tap on District drop down icon 4. Now Tap on State drop down icon and Observe | Expert is able to open State and District drop down at same time, under Post Advisory page. | Expert should not allow to open State and District drop down at same time, under Post Advisory page. | http://prntscr.com/i921i8 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Verified as on 5-2-2018
5-febb
75 | Both | Functional | HIgh | Loading icon continuoulsy appears on opening attached advisory pdf. | Expert has posted an advisory with attached pdf. | 1. User has logged in into his account 2. Open attached document of posted advisory and Observe | Loading icon continuoulsy appears on opening attached advisory pdf. | Loading icon should not appear on opening attached advisory pdf. | http://prntscr.com/ia9aqi | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [11 empty] | Done on both |  |  | Verified
76 | IOS | UI | Medium | Default audio appears on opening posted advisory with attached only video, only on IOS. | Expert has posted an advisory with attached video. | 1. Open posted advisory and Observe | Default audio appears on opening posted advisory with attached only video, only on IOS. | Default audio should not appear on opening posted advisory with attached only video, only on IOS. | http://prntscr.com/ia9av8 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Verified on IOS
77 | IOS | Functional | High | Application hangs on clicking Submit button after entering invalid email id, under 'My Profile' page. | Expert has logged in into his account. | 1. Tap on 'My Profile' icon 2. Enter invalid email and tap on 'Submit'button 3. Observe | Application hangs on clicking Submit button after entering invalid email id, under 'My Profile' page. | Validation message should appear on clicking Submit button after entering invalid email id, under 'My Profile' page. | http://prntscr.com/iaac3c | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Verified on IOS
78 | ANDROID | Functional | High | User is not able to update Name and Email under 'My Profile' page, only on Android. | Expert has logged in into his account. | 1. Tap on 'My Profile' icon 2. Tap on email field and Name field 3. Observe | Nothing happens on clicking on Email and Name text field, under 'My Profile' page, only on Android. | User should be able to update Name and Email under 'My Profile' page, only on Android. | http://prntscr.com/iaabka | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [11 empty] | Done |  |  | Verified
79 | IOS | UI | Medium | Became an expert' page title appears instead of 'Become an Expert'. | User has logged in into his account. | 1. Tap on Hamburger icon 2. Tap on 'Become an Expert' tab 3. Observe the page title. | Became an expert' page title appears instead of 'Become an Expert'. | Become an expert' page title should appear instead of 'Became an Expert'. | http://prntscr.com/iacpy3 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Verified on IOS
80 | IOS | Functional | Medium | Home' link is not functional, which appears under left side panel, only on IOS | User has logged in into his account. | 1. Tap on 'Q&A' icon 2. Tap on Hamburger icon 3. Tap on 'Home' link 3. Observe. | Home' link is not functional, which appears under left side panel. | Home' link should be functional, which appears under left side panel. | http://prntscr.com/iacqxb | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Same issue appears for 'Live Stock' link. | [9 empty] | Done | Verified on IOS
6-febb
81 | Both | UI | Medium | No validation message appears on clicking 'Redeem' button after entering unlimited digits under Pincode field under 'Prizes &Products' detail page. | User has logged in into his account. | 1. Tap on 'Prizes & Products' tab on left side panel. 2. Tap on any product 3. Enter unlimited digits under Pincode field and fill all other mandatory fields 4. Tap on 'Redeem' button and Observe. | No validation message appears on clicking 'Redeem' button after entering unlimited digits under Pincode field under 'Prizes &Products' detail page. | Proper validation message should appear on clicking 'Redeem' button after entering unlimited digits under Pincode field under 'Prizes &Products' detail page. | http://prntscr.com/iaq4lv | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [10 empty] | Done in iOS | Verified on IOS |  | Done in android | Verified
82 | Both | Functional | Medium | Redeemed total credits does not appear under Thank You confirmation page. | User has logged in into his account. | 1. Tap on 'Prizes & Products' tab on left side panel. 2. Tap on any product 3. Increase the quantity and fill all other mandatory fields 4. Tap on 'Redeem' button and Observe the credits field. | Redeemed total credits does not appear under Thank You confirmation page. | Redeemed total credits should appear under Thank You confirmation page. | http://prntscr.com/iaqzue | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [10 empty] | Done in iOS | Verified on IOS | Still Occurring on Android | Done in android | Verified
83 | Android | Functional | Medium | No validation message appears on clicking 'Submit' button after leaving district field blank, under 'My Profile' page. | User has logged in into his account. | 1. Tap on 'My Profile' icon 2. Fill all mandatory fields and leave District field blank 3. Tap on 'Submit' button and Observe | No validation message appears on clicking 'Submit' button after leaving district field blank, under 'My Profile' page. | Select District' validation message should appear on clicking 'Submit' button after leaving district field blank, under 'My Profile' page. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [13 empty] | Done | Verified
84 | Both | UI | Medium | States appears in english even after selecting language as 'Hindi'/ 'Punjabi' under Mandi rates page. | User has logged in into his account and has selected Hindi/Punjabi Language | 1. Goto 'Mandi' rates page 2. Tap on States drop down. 3 .Observe. | States appears in english even after selecting language as 'Hindi'/ 'Punjabi' under Mandi rates page. | States should appear in Hindi/Punjabi after selecting language as 'Hindi'/ 'Punjabi' under Mandi rates page. | http://prntscr.com/iatxcg | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [11 empty] | Data is coing from Government side so its not possible to show in Hindi and Punjabi. | Verified as per developer's comment.
85 | Both | Functional | Medium | Loading icon appears for a long time and no validation appears on clicking 'Submit' button after leaving District mandatory field blank, under 'Become an Expert' page. | User has logged in into his account. | 1. Tap on 'Become an Expert' tab 2. Fill all mandatory fields and attach photo , video and document 3. Now, leave District field blank 4. Tap on 'Submit' button 5. Observe | Loading icon appears for a long time and no validation appears on clicking 'Submit' button after leaving District mandatory field blank, under 'Become an Expert' page. | Proper validation message should appear on clicking 'Submit' button after leaving District mandatory field blank, under 'Become an Expert' page. | http://prntscr.com/iaursl | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [11 empty] | Done in iOS, for loader please check on other network. | Verified on IOS
86 | Android | UI | Low | Spelling mistakes appears in confirmation message which appears after submitting 'Become an Expert' form. | User has logged in into his account and has selected Hindi Language | 1. Tap on 'Become an Expert' tab 2. Fill all mandatory fields 3. Tap on 'Submit' button 4. Observe | Spelling mistakes appears in confirmation message which appears after submitting 'Become an Expert' form. | Spelling mistakes should not appear in confirmation message which appears after submitting 'Become an Expert' form and confirmation message should appear similar as shown in IOS. | http://prntscr.com/iavfcq | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [13 empty] | Done | Verified
7-Febb
87 | Android | Functional | Medium | Event gets added on selecting 'Event End Date' less than 'Event Start Date', under 'Add Event' page. | User has logged in into his account. | 1. Tap on 'Events' icon 2. Tap on 'Add Event' button 3. Select Event End Date less than Event Start Date 4. Fill all other mandatory fields 5. Click on 'Submit' button 6. Observe | Event gets added on selecting 'Event End Date' less than 'Event Start Date', under 'Add Event' page. | Event should not get added and proper validation message should appear on selecting 'Event End Date' less than 'Event Start Date' , under 'Add Event' page. | http://prntscr.com/htou9d | Iphone 6s(IOS 11), Android 7 | Android 7 | [13 empty] | Done | Verified
88 | Android | Functional | low | User is able to go to the next lines on tapping Enter icon without entering data in search field, under 'Change Location' section on left side panel. | User has logged in into his account. | 1. Tap on 'Hamburger' icon 2. Tap on 'Change Location' option 3. Tap on 'Choose Your State' search field 4. Tap 'Return' icon 5. Observe | User is able to go to the next lines on tapping Enter icon without entering data in search field, under 'Change Location' section on left side panel. | User should not allow to go to the next lines on tapping Enter icon without entering data under search field, under 'Change Location' section on left side panel. | http://prntscr.com/htpaxl | Iphone 6s(IOS 11), MI(Android version 6), Samsung(Android Version 7) | MI(Android version 6), Samsung(Android Version 7) | [13 empty] | Done | Verified
89 | IOS | UI | low | Home icon appears larger than other icons on the footer of the homepgae. | User has logged in into his account. | 1. Home page opens up 2. Observe | Home icon appears larger than other icons on the footer of the homepgae. | Home icon should not appear larger than other icons on the footer of the homepgae. | http://prntscr.com/ib9xko | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Verified on IOS
90 | IOS | UI | low | UI issues appear under drop down filter of Mandi Rates page. | User has logged in into his account. | 1. Tap on Mandi Rates icon 2. Tap on State drop down and Observe the partition lines. | UI issues appear under drop down filter of Mandi Rates page. | UI issues should get resolved as shown in screenshots, under drop down filter of Mandi Rates page. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Still Occurring on IOS Screenshot Reference: http://prntscr.com/idyx54 |  | Done | Verified
91 | IOS | UI | Medium | UI issue appears under Advisory detail screen. | User has logged in into his account. | 1. Tap on Advisory tab 2. Open any advisory 3. Observe | 1. Unwanted audio icon appears on opening any advisory detail screen. 2. Share icon is not aligned properly 3. Advisory text is not aligned properly. 4. Yellow line is not placed properly. | 1. Unwanted audio icon appears on opening any advisory detail screen. 2. Share icon should aligned according to the Update detail screen 3. Advisory text should be aligned properly. 4. Yellow line should placed properly | http://prntscr.com/ib8h45 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Still Occurring on IOS |  | Done | Still Occurring on IOS
92 | IOS | Functional | High | Nothing happens on clicking Expert query page after opening left side panel. | User has logged in into his account. | 1. Tap on Q&A icon 2. Tap on Ask Question button 3. Now tap on hamburger icon 4. Again tap on Expert Query page and Observe | Nothing happens on clicking Expert query page after opening left side panel. | Expert query page should open up even after opening left side panel. | http://prntscr.com/ib8k3m | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Still Occurring on IOS |  | Done | Verified
93 | IOS | UI | Low | Unwanted truncated line appears above the headings of Live Stock Page. | User has logged in into his account. | 1. Tap on 'Live Stock' icon 2. Observe the line on the headings. | Unwanted truncated line appears above the headings of Live Stock Page. | Unwanted truncated line should not appear above the headings of Live Stock Page. | http://prntscr.com/iba2qg | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | [10 empty] | Done | Verified on IOS
94 | IOS | UI | Low | Space below the buttons are not consistent, under 'Q&A' page. | User has logged in into his account. | 1. Tap on Q&A icon 2. Scroll down the page and Observe the spacing below the Write Answer and View All Answers button | Space below the buttons are not consistent, under 'Q&A' page. | Space below the buttons should be consistent, under 'Q&A' page. | http://prntscr.com/ibafr2 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Same issue appears under My Questions page. | [9 empty] | Done | Issue is still occurring under 'My Questions' page. |  | Done | Verified
95 | Both | UI | Medium | Tags appear in answer, under 'Organic and Natural' tab of 'Q&A' page. | User has logged in into his account. | 1. Tap on Q&A icon 2. Tap on 'Organic and Natural' tab 3. Observe | Tags appear in answer, under 'Organic and Natural' tab of 'Q&A' page. | Tags should not appear in answer, under 'Organic and Natural' tab of 'Q&A' page. | http://prntscr.com/ib9yg7 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | [10 empty] | Done in iOS | Verified on IOS |  | After 3rd scroll api will show error Please ask backend person for this | Mohit please resolve its from your end
96 | Android | Functional | High | Application vibrates on scrolling down the Organic and Natural page. | User has logged in into his account. | 1. Tap on Q&A icon 2. Tap on 'Organic and Natural' tab 3. Scroll down the page upto end and Observe | Application vibrates on scrolling down the Organic and Natural page. | Application should not vibrate on scrolling down the Organic and Natural page. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
12 febb
97 | Android | Functional | High | Error pop up opens up on opening advisory, under 'Advisory' page. | User has logged in into his account. | 1. Tap on 'Advisory' tab 2. Open any advisory and Observe | Error pop up opens up on opening advisory, under 'Advisory' page. | Error pop up should not open up on opening advisory, under 'Advisory' page. | [16 empty] | Not fromour side Api end issue response is not coming from server. That’s why its showimh error | Verified
98 | Both | Functional | Medium | No confirmation message appears on submitting any question/answer, under 'Q&A' page. | Expert has answered the question. | 1. Observe | No confirmation message appears on submitting any question/answer, under 'Q&A' page. | Proper confirmation message should appear on submitting any question/answer, under 'Q&A' page. | [16 empty] | it is because warning is coming because of null in device token please askbackend person | Verified
99 | Both | UI | Medium | Q&A icon does not get highlighted after clicking on 'Ask Questions' button. | User has logged in into his account. | 1. Tap on 'Q&A' icon 2. Tap on 'Ask Questions' button 3. Observe 'Q&A' icon | Q&A icon does not get highlighted after clicking on 'Ask Questions' button. | Q&A icon should get highlighted after clicking on 'Ask Questions' button. | [16 empty] | Already discussed on call | Closed
100 | Both | UI | Medium | Dogs category names appears in english even after selecting hindi language, under live stock page. | Open Apni Kheti App. | 1.Open apni kheti app. 2.Select language as Hindi. 3.Goto 'Live stock' page. 3.Scroll down. 4.Observe. | Dogs category names appears in english even after selecting hindi language, under live stock page. | Dogs category names should not appear in english after selecting hindi language, under live stock page. | http://prntscr.com/ic8vpx | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5),Android. | [13 empty] | it is coming from server right now it is fine. If its ic again coming in english so please akk backend persopn to look this issue
101 | Android | UI | Medium | Incorrect information appears on opening a weather page after selecting language as hindi. | Open Apni Kheti App. | 1.Open apni kheti ' app. 2.Select Hindi language. 3.Open weather page. 4.Observe. | Incorrect information appears on opening a weather page after selecting language as hindi. | Appropriate information should appear on opening a weather page after selecting language as hindi. | http://prntscr.com/idl546 | Iphone 6s(IOS version-11.2.5),Android. | Android. | [14 empty] | Verified
13-Febb
102 | IOS | Functional | High | Nothing happens on clicking Submit button after entering data in all mandatory fields, under Become An Expert' page. | User has logged in into his account | 1. User has filled Become an expert form 2. Tap on 'Submit'button and Observe | Nothing happens on clicking Submit button after entering data in all mandatory fields, under Become An Expert' page. | Confirmation message should appear on clicking Submit button after entering data in all mandatory fields, under Become An Expert' page. | http://prntscr.com/idz0gk | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5). | [13 empty] | Done | Verified as on 16-Febb
103 | IOS | UI | Medium | UI issue appears under 'Prizes & Products' page. | User has logged in into his account | 1. User is on 'Prize &Products' page 2. Open any product and Observe | 1. Incorrect spellings appears under Validation message 2. Validation message appears in english even after selecting Hindi or Punjabi language. 3. Unwanted space appears under Product detail page. | UI issue should get resolved as shown in screenshot. | http://prntscr.com/idz6qk | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5). | [13 empty] | Done | Verified as on 16-Febb
104 | Android | UI | Medium | UI issue appears under 'Prizes & Products' page. | User has logged in into his account | 1. User is on 'Prize &Products' page 2. Open any product and Observe | 1. Incorrect validation message appears on entering incorrect data in any mandatory field 2. Validation message always appears in english even after selecting Hindi Or Punjabi language 3. Unwanted Size field appears for every product. | 1. Correct validation message should appear on entering incorrect data in any mandatory field 2. Validation message should not appear in english after selecting Hindi Or Punjabi language 3. Unwanted Size field should not appear for every product. | http://prntscr.com/idzeh6 | Iphone 6s(IOS version-11.2.5),Android. | Android. | [13 empty] | Done | Verified as on 16-Febb
105 | Android | Functional | Medium | No validation message appears on clicking Redeem button without selecting Product size | User has logged in into his account | 1. User is on 'Prize &Products' page 2. Open any Tshirt 3. Fill all mandatory fields and leave size field blank 4. Tap on Redeem button and Observe | No validation message appears on clicking Redeem button without selecting Product size | Proper validation message should appear on clicking Redeem button without selecting Product size | http://prntscr.com/idzel9 | Iphone 6s(IOS version-11.2.5),Android. | Android.
106 | Android | Functional | High | User is redirecting to incorrect page on tapping Home icon under Prizes & Products detail page. | User has logged in into his account | 1. User is on 'Prize &Products' page 2. Open any Product 3. Tap on Home icon and Observe | User is redirecting to incorrect page on tapping Home icon under Prizes & Products detail page. | User should redireced to Home page on tapping Home icon under Prizes & Products detail page. | http://prntscr.com/idzgdu | Iphone 6s(IOS version-11.2.5),Android. | Android.
107 | IOS | Functional | Medium | Expert is not able to play audio again, under Preview Files page of Post Advisory page. | Expert has logged in into his account. | 1. Expert is on Post Advisory page 2. Fill data in all mandatory fields and attach audio and Video 3. Tap on Preview files and play audio 4. Now, play audio again and Observe | Expert is not able to play audio again, under Preview Files page of Post Advisory page. | Expert should be able to play audio again, under Preview Files page of Post Advisory page. | http://prntscr.com/idzlfv | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5). | [13 empty] | Done | Verified | Play icon should appear after completion of the audio
108 | IOS | UI | Medium | UI issue appears under 'Share Your Story With Us' page. | User has logged in into his account | 1. User is on 'Share Your Story With Us' page 2. Observe | UI issue appears under 'Share Your Story With Us' page. | UI issue should get resolved as shown in screenshot. | http://prntscr.com/idzo9g | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5). | [13 empty] | Done | Verified
109 | Both | UI | Medium | UI issue appears under Hisoty page of Prize & Products screen. | User has logged in into his account | 1. User is on 'Prize &Products' page 2. Tap on History icon and Observe | UI issue appears under Hisoty page of Prize & Products screen. | UI issue should get resolved as shown in screenshot. | http://prntscr.com/idzqpa | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5),Android. | [13 empty] | it is from server end data is coming in english please ask backend person for that point | Please discuss this with Vikram sir
110 | Both | UI | Low | Image icon appears even on attaching doc file with answer, under 'Q&A' page. | Expert has answered a question with attached doc | 1. Observe the answer in 'Q&A' page. | Image icon appears even on attaching doc file with answer, under 'Q&A' page. | Image icon should not appear on attaching doc file with answer, under 'Q&A' page. | http://prntscr.com/ie00pc | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5),Android. | [13 empty] | I have created this scenarion on both phone it is working fine on both. Please tell the scenario | Verified
15-2-2018
111 | Both | Functional | High | Attached video does not open up on clicking on user's name and also icon does not appear, under 'Unanswered' page. | Expert has logged in into his account. | 1. Tap on URA icon 2. Tap on Unanswered tab 3. Try to open video in android and Observe | 1. Android: Attached video does not open up on clicking on user's name and also icon does not appear 2. IOS: Only video icon is missing under Unanswered page | 1. Android: Attached video should open up on clicking on user's name and also icon should appear 2. IOS: video icon should appear under Unanswered page | http://prntscr.com/iexthd | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5),Android. | [13 empty] | Done in ios | Still Ocurring Mohit please make it similar as in Q&A page.
112 | IOS | Functional | High | Attached audio is not audible, under Q&A page. | Expert has logged in into his account. | 1. Tap on URA icon 2. Tap on Unanswered tab 3. Try to open audio and Observe | Attached audio is not audible, under Q&A page. | Attached audio should be audible, under Q&A/ Unanswered page. | http://prntscr.com/iexyow | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5) | Same issue appears under Crops page | [12 empty] | Not coming I had checked this . | Verified
113 | Android | Functional | Medium | Video icon still appears played even after the completion of the video, under Q&A page. | User has logged in into his account. | 1.Tap on 'Q&A' icon. 2.Open any posted video. 3.Play video till the end 4.Observe. | Video icon still appears played even after the completion of the video, under Q&A page. | Video icon should not appear played after the completion of the video, under Q&A page. | http://prntscr.com/iey2to | Iphone 6s(IOS version-11.2.5),Android. | Android.
16-2-2018
114 | Android | UI | Low | Spelling mistakes appears in validation message which appears on clicking Submit button after entering number less than 10 digits, under 'Share Your Story With Us' page | User has logged in into his account and has selected Punjabi lanugage. | 1. Tap on 'Progressive Farmers' icon 2. Tap on Share Your Story button 3. Fill all mandatory fields and enter number less than 10 digits 4.Tap Submit button and Observe | Spelling mistakes appears in validation message which appears on clicking Submit button after entering number less than 10 digits, under 'Share Your Story With Us' page | Spelling mistake should not appear in validation message which appears on clicking Submit button after entering number less than 10 digits, under 'Share Your Story With Us' page | http://prntscr.com/ifhmqe | Iphone 6s(IOS version-11.2.5),Android. | Android.
115 | Both | Functional | High | No preview Available' page opens up on opening attached advisory PDF. | User has logged in into his account. | 1. Open posted advisory pdf and Observe | No preview Available page opens up on opening attached advisory PDF. | Attached pdf should open up on opening attached advisory PDF. | http://prntscr.com/ifg3c4 | Iphone 6s(IOS version-11.2.5),Android. | Iphone 6s(IOS version-11.2.5),Android.
116 | Android. | Functional | High | Application hangs on scrolling down the Answered page. | Expert has logged in into his account. | 1. Tap on URA icon 2. Tap on answered tab 3. Scroll down the page upto specific question and observe | Application hangs on scrolling down the Answered page. | Application should not hang on scrolling down the Answered page. | http://prntscr.com/ifidf0 | Iphone 6s(IOS version-11.2.5),Android. | Android.
117 | Android. | Functional | High | Full Recommend list does not appear, under Recommend page only on Android. | Expert has logged in into his account. | 1. Tap on URA icon 2. Tap on Recommend tab 3. Scroll down the page and observe | Full Recommend list does not appear, under Recommend page only on Android. | Full Recommend list should appear, under Recommend page only on Android. | http://prntscr.com/ifie3a | Iphone 6s(IOS version-11.2.5),Android. | Android. | Same issue appears for Unanswered page

## Pending_Defects
Defect_Id | Issue Description | Pre Requisties | Steps To Recreate | Actual Result | Expected Result | Screenshot Reference | Tested On | Affected On | Dev Comments | Retesting as on 18-1-2018 | Dev Comments | Retestng as on 22-1-2018 | Dev Comments | Retestng as on 25-1-2018 | Dev Comments | Retestng as on 31-1-2018
6 | UI issue appears under OTP page. | Open Apni Kheti app. | 1. Open Apni Kheti app in Android 2. Enter number and Tap on Submit' button 3. Observe the OTP page 4. Repeat above steps on IOS and Observe the OTP page | 1. Inconsistent place holder text appears in IOS and Android respectively 2. OTP appears in small case under 'Didn't receive the Otp?' text under IOS. 3. Label of Submit button appears in small case in IOS whereas it appears in upper case in Android. 4. Image on the top of the page has different sizes in IOS and Android. | 1. 'Enter OTP' place holder text should appear in IOS 2. OTP should appears in upper case under 'Didn't receive the Otp?' text under IOS. 3. Label of Submit button should appear in upper case. 4. Image on the top of the page should be of same size as in android. | http://prntscr.com/i12mzw | Iphone 6, 6s(IOS 11), Android 7 | Iphone 6, 6s(IOS 11) |  | Still Occurring on IOS as on 18-1-2018 | Done | Still Occurring as 'Image on the top of the page should be of same size as in android.' | I have check in android image size is same it depend upon screen size also please check it on same screen size and tell us if you still found the issue | Still Occurring 1. Content under OTP page appear small as compare to image, on IOS that is looking quite different. So, decrease the size of the image 2. Content under OTP page should be centrally aligned in IOS and Android. | Done | Still Occurring as Content under OTP page should be centrally aligned in Android.
15 | Image disappears on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | 1. User has logged in into his account. | 1. Tap on 'Live Stock' icon 2. Select 'HF(HOLSTEIN FRESIAN) cow 3. Tap on 'Diseases and Treatment' tab 4. Scroll down the section 5. Scroll up the section and Observe the image | Image disappears on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | Image should not get disappear on scrolling down the page after clicking on 'Diseases and Treatment' tab, under 'Live Stocks' page. | http://prntscr.com/i1m10d | Iphone 6, 6s(IOS 11),Android 7 | Iphone 6, 6s(IOS 11) | I am not doing anything is this i just show the link in webview it is not from my side | We have checked the web view link in Safari browser and it is working fine. It is also working fine in Android browser and Android App. |  | Mohit Kindly Comment. |  | Still Occurring as on 25-1-2018 | it Is coming in ios version 11 not in lower version we found some olution because it is unexpected issue | Still Occurring. This issue should get resolve for latest versions ASAP.
19 | Null value appears instead of name of the user who has posted the question, under 'Q&A' page. | Expert has logged in into his account. | 1. Tap on Q&A section 2. Scroll down the page and Observe | Null value appears instead of name of the user who has posted the question, under 'Q&A' page. | User name should appear instead of Null value, under 'Q&A' page. | http://prntscr.com/i212q9 | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Iphone 6(IOS 11.2), 6s(IOS 11.1),Android 7 | Server End |  |  | Still occurring.This is not from server end. Please resolve it ASAP. | As discussed in group it is not from our side
26 | UI issue appears under Post Advisory page. | 1. Expert has logged in into his account. 2. Expert has selected Hindi Language | 1. Tap on 'Post Advisory' tab under left side panel 2. Observe Placeholder text for text field 3. Now, fill all mandatory fields and leave Text mandatory field blank 4. Tap on 'Submit' button 5. Observe 6. Now select language 'Punjabi' 7. Tap on 'Post Advisory' tab 8. Observe the Placeholder text for State field and 'Text' field. 9. Leave State field blank 10. Tap on Submit button and Observe Validation message. | UI issue appears under Post Advisory page. | UI issue should get resolved as shown in attached screenshot. | http://prntscr.com/i3rp1n | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). |  |  |  |  | Done | Still Occurring. Screenshot Reference: http://prntscr.com/i59p7e | Done | Verified as on IOS on 31-1-2018 Still Occurring on Android.
28 | Notification' count beyond 99 is not increasing , under Notification bell icon. | Expert has logged in into his account. | 1. Observe 'Notification' count after 99 count. | Notification' count beyond 99 is not increasing , under Notification bell icon. | Notification' count beyond 99 should increase , under Notification bell icon. | http://prntscr.com/i3ue60 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) |  |  |  |  | in this we have show + sign when notification ocunter greater than 99 as disscussed with hunar sir | Still Occurring as on 25-1-2018 | Done
29 | Posted advisory by expert does not appear under 'Advisory' subtab of 'Updates'tab. | Expert has logged in into his account. | 1. Tap on 'Post Advisory' tab under left side panel 2. Post a advisory 3. Observe the posted advisory under 'Advisory' section of Apni Kheti' app. | Submitted Succesfully' Cofirmation message appears but posted advisory does not appear under 'Advisory' subtab. | Posted advisory by expert should appear under 'Advisory' subtab of 'Updates'tab. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). |  |  |  |  | Done | Still Occurring as on 25-1-2018 | as discussed on phone . It is shown on advisory section | Verified on IOS but Still Occurring on Android.
31 | Inconsistent 'Unfortunately, Apni Kheti has stopped' validation pop up opens up on leaving phone in Ideal State, only on Android. | Expert has logged in into his account. | 1.Leave phone in Ideal state 2. Observe | Inconsistent 'Unfortunately, Apni Kheti has stopped' validation pop up opens up on leaving phone in Ideal State, only on Android. | Unfortunately, Apni Kheti has stopped' validation pop up should not appear on leaving phone in Ideal State, only on Android. |  | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). |  |  |  |  | Unable to create this issue |  |  | Still Occurring as on 31-1-2018
33 | Page scrolls down automatically after clicking on 'My Profile' tab, only on Android. | User has logged in into his account. | 1. Tap on 'My Profile' tab. 2. Observe | Page scrolls down automatically after clicking on 'My Profile' tab, only on Android. | Page should not get scrolled down after clicking on 'My Profile' tab, only on Android. | http://prntscr.com/i4b6rf | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
34 | Constrain' option does not appear after uploading profile image under 'My Profile' page, only on Android. | User has logged in into his account. | 1. Tap on 'My Profile' tab. 2. Upload an image from gallery 3. Observe | Constrain' option does not appear after uploading profile image under 'My Profile' page, only on Android. | Constrain' option should appear after uploading profile image under 'My Profile' page, only on Android. | http://prntscr.com/i4cf0l | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
35 | Updated profile image does not appear on another phone for the same user, under 'My Profile' page. | Same user has logged in in two devices. | 1.Tap on 'My Profile' tab. 2. Upload an image from gallery 3. Tap on 'Submit' button 4. Now observe the profile image on another phone. | Updated profile image does not appear on another phone for the same user, under 'My Profile' page. | Updated profile image should appear on another phone for the same user, under 'My Profile' page. | http://prntscr.com/i4exij | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
37 | Validation message appears on leaving non mandatory 'District' field blank , under 'Post Advisory' page, only on IOS | Expert has logged in into his account. | 1. Tap on 'Post Advisory' tab on left side panel 2. Leave district field blank and fill all other mandatory fields 3. Tap on 'Submit' button 4. Observe | Please select state and district.' validation message appears on leaving non mandatory 'District' field blank, under 'Post Advisory' page. | No such validation message should appear on leaving 'District' field blank as it is not a mandatory field, under 'Post Advisory' page. | http://prntscr.com/i59f5d | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | it is mandetory that’s why I show the validation message | [6 empty] | Still Occurring as District field is not mandatory please resolve this issue.
38 | Unwanted text appears in notification received about advisory, only on Android | 1. User has posted a question 2. Expert has answered a question | 1.User received a notification 2. Observe | Unwanted text appears in notification received about advisory, only on Android | No such unwanted text should appear in notification received about advisory, only on Android | http://prntscr.com/i5adwk | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7). | [7 empty] | Still Occurring on Android.
39 | Null Values appear after tapping on 'Weather' icon. | New user has logged in into his account. | 1. Enter all profile information 2. Tap on 'Weather' icon 3. Observe | Null Values appear after tapping on 'Weather' icon. | Null Values should not appear after tapping on 'Weather' icon. | http://prntscr.com/i701ak | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Resolve all the UI issues regarding this page 1. Place degree icon with 27 2. Screenshot Reference: http://prntscr.com/i7zucx
40 | Heading appears in English even after selecting hindi or punjabi language, under Reference Code pop up. | 1. User has selected Hindi language and New user has logged in into his account. | 1. Observe the reference code heading. | Heading appears in English even after selecting hindi or punjabi language, under Reference Code pop up. | Heading should appears in hindi or punjabi on selecting hindi or punjabi language, under Reference Code pop up. | http://prntscr.com/i701w9 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1) | Done | [6 empty] | Refer kiya code' header text appears instead of Reference code in Hindi.
44 | Attached document does not appear along with answer after answering a question. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Observe the answer sent by expert. | Attached document does not appear along with answer after answering a question. | Attached answer document should appear after answering a question. | http://prntscr.com/i7hoh8 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
45 | Default video and audio appears under 'Preview Files' page after attaching document, under 'Q&A' section. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Tap on 'Preview files' tab 2. Observe | Default video and audio appears under 'Preview Files' page after attaching only document, under 'Q&A' section. | Only attached document should appear under 'Preview Files' page after attaching document, under 'Q&A' section. | http://prntscr.com/i7hws5 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1)
46 | Close' icon still appears after removing the attached document, under 'Attach' pop up of 'Q&A' section. | Expert has attached any of these pdf/excel/word/CSV document. | 1. Tap on 'Close' icon of attached document 2. Remove the document and Observe | Close' icon still appears after removing the attached document, under 'Attach' pop up of 'Q&A' section. | Close' icon should not appear after removing the attached document, under 'Attach' pop up of 'Q&A' section. | http://prntscr.com/i7i0eu | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1)
47 | Sun appears even after weather is cloudy or rainy, under 'Forecast Weather' page. | User has logged in into his account. | 1. Tap on 'Weather' icon 2. Select Location and Observe | Sun appears even after weather is cloudy or rainy, under 'Forecast Weather' page. | Sun should not appear when weather is cloudy or rainy, under 'Forecast Weather' page. | http://prntscr.com/i7l5oy | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
48 | Posted advisory by expert appears many time, under Advisory page. | Expert has logged in into his account. | 1. Expert has posted a advisory 2. Now, Go to Updates 3. Tap on 'Advisory' tab 4. Observe | Posted advisory by expert appears many time, under Advisory page. | Posted advisory by expert should not appear many time, under Advisory page. | http://prntscr.com/i7zo4l | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
49 | Full stop appears in the end of validation message, under Post Advisory page. | Expert has logged in into his account and has selected hindi language. | 1. Expert is on Post Advisory page 2. Leave Advisory field blank and fill all other mandatory fields 3. Tap on submit button and Observe | Full stop appears in the end of validation message, under Post Advisory page. | Full stop should not appear in the end of validation message, under Post Advisory page. | http://prntscr.com/i7zo9k | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1)
50 | On selecting single district some other districts get selected automatically, under 'Post Advisory' page only on IOS. | Expert has logged in into his account. | 1. Expert is on Post Advisory page 2. fill all mandatory fields and select State>>Punjab, District>> Amritsar 3. observe Ferozpur , Mansa and Sangrur districts | On selecting single district some other districts get selected automatically, under 'Post Advisory' page only on IOS. | Only selected district should get checked, under 'Post Advisory' page only on IOS. | http://prntscr.com/i80dl6 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1),
51 | Irrelevant validation message appears on leaving Region field blank, under 'Share Your Story With Us' page. | Expert has logged in into his account and selected Hindi/Punjabi lanugage | 1. Expert is on 'Share Your Story With Us' page. 2. fill all mandatory fields and Leave Region field blank 3. Tap on 'Submit' button and Observe | Irrelevant validation message appears on leaving Region field blank, under 'Share Your Story With Us' page. | Appropriate validation message should appear on leaving Region field blank, under 'Share Your Story With Us' page. | http://prntscr.com/i83n10 | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
52 | No validation message appears on entering invalid mobile number, under 'Share Your Story With Us' page. | Expert has logged in into his account | 1. Expert is on 'Share Your Story With Us' page. 2. fill all mandatory fields and enter invalid number 3. Tap on 'Submit' button and Observe | No validation message appears on entering invalid mobile number, under 'Share Your Story With Us' page. | Proper validation message should appear on entering invalid mobile number, under 'Share Your Story With Us' page. | http://prntscr.com/i83jbb | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
53 | Unwanted tags appear in notification received under 'Notification' page of user only on Android. | Expert has logged in into his account | 1. Another expert has posted a advisory 2. Tap on Notification and Observe | Unwanted tags appear in notification received under 'Notification' page of user only on Android. | Unwanted tags should not appear in notification received under 'Notification' page of user only on Android. | http://prntscr.com/i83kao | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Samsung Galaxy S5 (Android 7).
54 | Inconsistent button appears on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | Expert has logged in into his account | 1. Tap on Hamburger icon on Android 2. Tap on Settings tab 3. Tap on Logout button and Observe 4. Repeat above steps on IOS. | Inconsistent button appears on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | Consistent button should appear on confirmation pop up which opens up after clicking on 'Logout' tab under Android and IOS | http://prntscr.com/i83rvr | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
55 | Spelling mistake appears in validations, under 'Share Your Story With Us' page. | Expert has logged in into his account | 1. Expert is on 'Share Your Story With Us' page. 2. fill all fields and leave mobile number and donot upload image 3. Tap on Submit button and Observe | Spelling mistake appears in validations, under 'Share Your Story With Us' page. | Spelling mistake should not appear in validations, under 'Share Your Story With Us' page. | http://prntscr.com/i83wzh | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).
56 | UAR' appears in english even after selecting Hindi/Punjabi, under Header of the page. | Expert has logged in into his account | 1. Select Hindi /Punajbi Language 2. Observe the UAR section. | UAR' appears in english even after selecting Hindi/Punjabi, under Header of the page. | UAR' should not appear in english after selecting Hindi/Punjabi, under Header of the page. | http://prntscr.com/i840hz | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7). | Iphone 6(IOS 11.2), 6s(IOS 11.1), Samsung Galaxy S5 (Android 7).